## Product Backlog
Backlog ID | User Story / Requirement | Owner | Priority | Sprint
PB-01 | Gather requirements from students, faculty, parents and stakeholders | Product Owner | High | Sprint-1
PB-02 | Create Software Requirement Specification (SRS) | Product Owner | High | Sprint-1
PB-03 | Design system architecture for Online Learning Portal | DevOps Engineer | High | Sprint-1
PB-04 | Create database schema for students, faculty, attendance and results | Backend Developer | High | Sprint-1
PB-05 | Setup GitHub repository and branching strategy | DevOps Engineer | High | Sprint-1
PB-06 | Install and configure Jenkins for CI/CD | DevOps Engineer | High | Sprint-1
PB-07 | As a student, I want to register and login securely | Frontend & Backend Developer | High | Sprint-2
PB-08 | As a faculty member, I want to login securely | Frontend & Backend Developer | High | Sprint-2
PB-09 | As a parent, I want to login securely | Frontend & Backend Developer | High | Sprint-2
PB-10 | Implement role-based access control | Backend Developer | High | Sprint-2
PB-11 | As a student, I want to view my dashboard | Frontend Developer | Medium | Sprint-2
PB-12 | As a student, I want to view attendance details | Frontend & Backend Developer | High | Sprint-3
PB-13 | As a faculty member, I want to enter attendance | Frontend & Backend Developer | High | Sprint-3
PB-14 | As a student, I want to view assignments | Frontend & Backend Developer | High | Sprint-3
PB-15 | As a faculty member, I want to upload assignments | Frontend & Backend Developer | Medium | Sprint-3
PB-16 | As a student, I want to view semester results | Frontend & Backend Developer | High | Sprint-3
PB-17 | As a parent, I want to monitor student progress | Frontend & Backend Developer | Medium | Sprint-3
PB-18 | Implement notification module | Backend Developer | Medium | Sprint-3
PB-19 | Create automated test cases | QA Engineer | High | Sprint-4
PB-20 | Perform functional and API testing | QA Engineer | High | Sprint-4
PB-21 | Containerize application using Docker | DevOps Engineer | High | Sprint-4
PB-22 | Build Jenkins CI/CD pipeline | DevOps Engineer | High | Sprint-4
PB-23 | Deploy application to cloud infrastructure | Cloud & Release Engineer | High | Sprint-4
PB-24 | Configure Prometheus and Grafana monitoring | Cloud & Release Engineer | Medium | Sprint-4
PB-25 | Prepare project documentation and sprint reports | Scrum Master | Medium | Sprint-4