## Sheet1
Team Zeta
Online Learning Platform
Team Capacity and Sprint Allocation
S.No | Member Name | Role | Sprint Focus | Points/ Sprint | Availability | Status
1 | T.Bhanu | Product Owner | Backlog , Planning | 8 | 100% | Active
2 | Puneet Kumar | Scrum Master | Sprint Allocation and Management | 10 | 100% | Active
3 | Vamshi | DevOps Engineer | Architechture and Design | 12 | 100% | Active
4 | T.Bhanu | Frontend Dev | UI/UX & Frontend Development | 13 | 100% | Active
5 | Revan Krsihna | Backend Dev | API & Database Development | 14 | 90% | Active
6 | Sathwik, Kumar | Cloud & Release Enginner | CI/CD, Deployment & Monitoring | 9 | 90% | Active
7 | Nissar | QA/Test Engineer | Testing & Quality Assurance | 11 | 100% | Active
SPRINT PLAN — 4 SPRINTS
Sprint # | Sprint Goal | Start Date | End Date | Duration | Committed Pts | Completed Pts | % Done | Velocity | Defects Found | Defects Fixed | Carry Over | Status | Stakeholder Review | Notes
Sprint 1 | Requirement Analysis and Environment Setup | 2026-06-16 | 2026-06-30 | 14 Days | 70 | 68 | 97% | 68 | 2 | 2 | 2 | Completed | 2026-06-17 | SRS, Product Backlog, Sprint Plan completed ✓
Sprint 2 | Authetication & User Management | 2026-07-01 | 2026-07-14 | 14 Days | 75 | 45 | 0% | 0 | 0 | 0 | 30 | In Progress | 2026-07-02 | Authentication and Registration Module
Sprint 3 | Academic Management | 2026-07-15 | 2026-07-28 | 14 Days | 80 | 0 | 0% | 0 | 0 | 0 | 80 | Planned | 2026-07-16 | Mangement System
Sprint 4 | Devops & Deployment | 2026-07-29 | 2026-08-11 | 14 Days | 85 | 0 | 0% | 0 | 0 | 0 | 85 | Planned | 2026-07-30 | Production Deployment and Monitoring Dashboard
TOTALS |  |  |  |  | 310 | 113 | 24.25% | 17 | 2 | 2 | 197
Sprint 1 Daily Log – Requirement Analysis & Planning
Date | Team Member | Activity Performed | Pts | Help Needed | Status
2026-06-17 | Bhanu (PO) | Conducted project kickoff meeting and gathered initial stakeholder requirements | 10 | No | Completed
2026-06-17 | Puneet (SM) | Organized sprint planning meeting and defined sprint goals | 6 | No | Completed
2026-06-18 | Bhanu (PO) | Identified core features and documented business requirements | 10 | No | Completed
2026-06-18 | Puneet (SM) | Created sprint board and assigned responsibilities | 5 | No | Completed
2026-06-19 | Bhanu (PO) | Prepared user stories for Artists, Customers, and Administrators | 10 | No | Completed
2026-06-19 | Vamshi (Architect) | Participated in requirement discussions and identified technical constraints | 6 | No | Completed
2026-06-20 | Bhanu (PO) | Prioritized backlog items based on business value and stakeholder needs | 8 | No | Completed
2026-06-20 | Puneet (SM) | Reviewed sprint progress and updated sprint backlog | 5 | No | Completed
2026-06-21 | Entire Team | Requirement review meeting and project scope discussion | 8 | No | Completed
2026-06-22 | Bhanu (PO) | Finalized Product Backlog and acceptance criteria | 10 | No | Completed
2026-06-22 | Puneet (SM) | Prepared Sprint Review presentation and Sprint 2 planning notes | 4 | No | Completed
2026-06-23 | Entire Team | Sprint Review with stakeholders and approval of Sprint 2 activities | 6 | No | Completed
| Sprint 1 Summary |  |  | Sprint 1 Deliverables
| Metric | Value |  | Deliverable | Status
| Sprint Goal | Requirement Analysis & Planning |  | Software Requirement Specification (SRS) | Completed
| Sprint Duration | 17 Jun 2026 – 30 Jun 2026 |  | Product Backlog | Completed
| Committed Story Points | 70 |  | User Stories | Completed
| Completed Story Points | 68 |  | Sprint Plan | Completed
| Remaining Story Points | 2 |  | Stakeholder Approval | Completed
| Completion Percentage | 97%
| Defects Found | 2
| Defects Fixed | 2
| Carry Over | 2
| Status | Completed
Formulas:
Stakeholder Review = (Table4[[#This Row],[Start Date]] +1)

## Sheet2
Online Learning Platform
Team Capacity and Sprint Allocation
S.No | Member Name | Role | Sprint Focus | Points/ Sprint | Availability | Status
1 | T.Bhanu | Product Owner | Backlog , Planning | 8 | 100% | Active
2 | Puneet Kumar | Scrum Master | Sprint Allocation and Management | 10 | 100% | Active
3 | Vamshi | DevOps Engineer | Architechture and Design | 12 | 100% | Active
4 | T.Bhanu | Frontend Dev | UI/UX & Frontend Development | 13 | 100% | Active
5 | Revan Krsihna | Backend Dev | API & Database Development | 14 | 90% | Active
6 | Sathwik, Kumar | Cloud & Release Enginner | CI/CD, Deployment & Monitoring | 9 | 90% | Active
7 | Nissar | QA/Test Engineer | Testing & Quality Assurance | 11 | 100% | Active
SPRINT PLAN — 4 SPRINTS
Sprint # | Sprint Goal | Start Date | End Date | Duration | Committed Pts | Completed Pts | % Done | Velocity | Defects Found | Defects Fixed | Carry Over | Status | Stakeholder Review | Notes
Sprint 1 | Requirement Analysis and Environment Setup | 2026-06-16 | 2026-06-30 | 14 Days | 70 | 68 | 97% | 68 | 2 | 2 | 2 | Completed | 2026-06-17 | SRS, Product Backlog, Sprint Plan completed ✓
Sprint 2 | Authetication & User Management | 2026-07-01 | 2026-07-14 | 14 Days | 75 | 45 | 0% | 0 | 0 | 0 | 30 | In Progress | 2026-07-02 | Authentication and Registration Module
Sprint 3 | Academic Management | 2026-07-15 | 2026-07-28 | 14 Days | 80 | 0 | 0% | 0 | 0 | 0 | 80 | Planned | 2026-07-16 | Mangement System
Sprint 4 | Devops & Deployment | 2026-07-29 | 2026-08-11 | 14 Days | 85 | 0 | 0% | 0 | 0 | 0 | 85 | Planned | 2026-07-30 | Production Deployment and Monitoring Dashboard
TOTALS |  |  |  |  | 310 | 113 | 24.25% | 17 | 2 | 2 | 197
Sprint 1 Daily Log – Requirement Analysis & Planning
Date | Team Member | Activity Performed | Pts | Help Needed | Status
2026-06-17 | Bhanu (PO) | Conducted project kickoff meeting and gathered initial stakeholder requirements | 10 | No | Completed
2026-06-17 | Puneet (SM) | Organized sprint planning meeting and defined sprint goals | 6 | No | Completed
2026-06-18 | Bhanu (PO) | Identified core features and documented business requirements | 10 | No | Completed
2026-06-18 | Puneet (SM) | Created sprint board and assigned responsibilities | 5 | No | Completed
2026-06-19 | Bhanu (PO) | Prepared user stories for Artists, Customers, and Administrators | 10 | No | Completed
2026-06-19 | Vamshi (Architect) | Participated in requirement discussions and identified technical constraints | 6 | No | Completed
2026-06-20 | Bhanu (PO) | Prioritized backlog items based on business value and stakeholder needs | 8 | No | Completed
2026-06-20 | Puneet (SM) | Reviewed sprint progress and updated sprint backlog | 5 | No | Completed
2026-06-21 | Entire Team | Requirement review meeting and project scope discussion | 8 | No | Completed
2026-06-22 | Bhanu (PO) | Finalized Product Backlog and acceptance criteria | 10 | No | Completed
2026-06-22 | Puneet (SM) | Prepared Sprint Review presentation and Sprint 2 planning notes | 4 | No | Completed
2026-06-23 | Entire Team | Sprint Review with stakeholders and approval of Sprint 2 activities | 6 | No | Completed
| Sprint 1 Summary |  |  | Sprint 1 Deliverables
| Metric | Value |  | Deliverable | Status
| Sprint Goal | Requirement Analysis & Planning |  | Software Requirement Specification (SRS) | Completed
| Sprint Duration | 17 Jun 2026 – 30 Jun 2026 |  | Product Backlog | Completed
| Committed Story Points | 70 |  | User Stories | Completed
| Completed Story Points | 68 |  | Sprint Plan | Completed
| Remaining Story Points | 2 |  | Stakeholder Approval | Completed
| Completion Percentage | 97%
| Defects Found | 2
| Defects Fixed | 2
| Carry Over | 2
| Status | Completed
Formulas:
Stakeholder Review = (Table420[[#This Row],[Start Date]] +1)

## Sheet3
Sprint Information |  | Product Backlog Progress |  | Completed Product Backlogs
|  |  |  | Backlog ID | Feature
Item | Details | Metric | Count | PB-03 | System Architecture Design
Sprint | Sprint 1 | Total Product Backlogs | 15 | PB-04 | Documentation, UML& DFD Diagrams
Sprint Duration | 16 June 2026 – 30 June 2026 | Backlogs Completed | 15 | PB-05 | Login UI & ER Diagram
Sprint Goal | Complete System Design, Documentation, and Frontend Prototype | Backlogs In Progress | 0 | PB-12 | GitHub Repository & Version Control Setup
Sprint Status | Completed | Backlogs Pending | 0
Sprint Deliverables
Team Contributions |  | Sprint 2 Summary
Team Member | Contribution | Metric | Value | Deliverable | Status
Bhanu (Product Owner) | Requirement validation, backlog refinement, stakeholder communication | Story Points Committed | 75 | System Architecture Diagram | Completed
Punnet (Scrum Master) | Sprint planning, sprint review, progress tracking | Story Points Completed | 73 | DFD Level 0 | Completed
Vamshi (System Architect) | System Architecture, UML & DFD preparation | Story Points Remaining | 2 | DFD Level 1 | Completed
Bhanu (Frontend Developer) | Developing complete frontend UI | Sprint Completion | 97% | DFD Level 2 | Completed
Vamshi (DevOps Engineer) | Configured GitHub repository, project structure, deployment strategy, DevOps workflow documentation |  |  | UML Diagram | Completed
Nissar (QA Engineer) | Reviewed UI, validated documentation, prepared initial test cases |  |  | Database Design (ER Diagram) | Completed
|  |  |  | Frontend Prototype | Completed

## Sheet4
Sprint Information |  | Product Backlog Progress |  | Completed Product Backlogs
Item | Details | Metric | Count | Backlog ID | Feature
Sprint | Sprint 2 | Total Product Backlogs | 15 | PB-07 | As a student, I want to register and login securely
Sprint Duration | 1 July 2026 – 14 July 2026 | Backlogs Completed | 8 | PB-08 | As a faculty member, I want to login securely
Sprint Goal | Authentication & User Management | Backlogs In Progress | 4
Sprint Status | Completed | Backlogs Pending | 3
Team Contributions |  | Sprint 1 Summary |  | Sprint Deliverables
Team Member | Contribution | Metric | Value | Deliverable | Status
Bhanu (Frontend Developer) | Student Login Module, Faculty Login Module, Parent Login Module, User Registration Module | Story Points Committed | 75 | Student Login Module | Completed
Punnet (Scrum Master) | Sprint planning, sprint review, progress tracking | Story Points Completed | 73 | Faculty Login Module | Completed
Nissar (QA Engineer) | Prepared initial test cases, Password Recovery Functionality | Story Points Remaining | 2 | Parent Login Module | In Progress
|  | Sprint Completion | 97% | User Registration Module | In Progress
|  |  |  | Password Recovery Functionality | In Progress
|  |  |  | Testing | In Progress
|  |  |  | Working Authentication and User Management System | Planned

## Sheet5
Sprint Information |  | Product Backlog Progress |  | Completed Product Backlogs
Item | Details | Metric | Count | Backlog ID | Feature
Sprint | Sprint 3 | Total Product Backlogs | 15 | PB-07 | As a student, I want to register and login securely
Sprint Duration | 29 July 2026 – 12 Aug 2026 | Backlogs Completed | 8 | PB-08 | As a faculty member, I want to login securely
Sprint Goal | front end modules | Backlogs In Progress | 4
Sprint Status | Completed | Backlogs Pending | 3
Team Contributions |  | Sprint 1 Summary |  | Sprint Deliverables
Team Member | Contribution | Metric | Value | Deliverable | Status
Bhanu (Frontend Developer) | Faculty,Parent login ,Attendance Module, Assignment Module,Results Module | Story Points Committed | 75 | Student Login Module | Completed
Nissar (QA Engineer) | Prepared initial test cases, Password Recovery Functionality | Story Points Completed | 73 | Faculty Login Module | Completed
|  | Story Points Remaining | 2 | Parent Login Module | completed
|  | Sprint Completion | 97% | User Registration Module | completed
|  |  |  | Password Recovery Functionality | completed
|  |  |  | Testing | In Progress
|  |  |  | Backend | Planned
|  |  |  | Deployment | Planned